## Sitemap
Address | Section | Type | Instances | Effort | Hours | Migrate? | Notes
CORE PAGES
sofarocean.com/ | Homepage | Static | 1 | High | 24 | Yes | Persona entry (Shipping¦Science¦Defence), product overview, stats snapshot, demo CTA
sofarocean.com/support | Support | Static | 1 | Medium | 8 | Yes | Support hub/portal entry
sofarocean.com/search | Utility | Static | 1 | Low | 4 | Yes | Site search page
SOLUTIONS — VOYAGE INTELLIGENCE (WAYFINDER)
sofarocean.com/solutions/voyage-intelligence | Wayfinder | Static | 1 | High | 20 | Yes | Product overview: core features, benefits, ROI; persona-tailored for fleets & operators
sofarocean.com/solutions/voyage-intelligence/vessel-performance-model | Wayfinder – VPM | Static | 1 | Medium | 10 | Yes | Vessel Performance Model sub-page
sofarocean.com/solutions/voyage-intelligence/demos | Wayfinder – Demos | Static | 1 | Medium | 8 | Yes | Interactive demos / embed
sofarocean.com/solutions/voyage-intelligence/use-cases/[slug] | Wayfinder – Use Cases | Template | 3 | Medium | 8 | Yes | Use case pages for Wayfinder
sofarocean.com/solutions/voyage-intelligence/mpa | Wayfinder – MPA | Static | 1 | Medium | 8 | Yes | MPA sub-page
SOLUTIONS — OCEAN SENSOR PLATFORM (SPOTTER)
sofarocean.com/solutions/ocean-sensor-platform | Spotter | Static | 1 | High | 20 | Yes | Product overview: data types, sensors, software, hardware specs, durability, scalability
sofarocean.com/solutions/ocean-sensor-platform/network-map | Spotter – Network Map | Static | 1 | Medium | 10 | Yes | Interactive Spotter network map
sofarocean.com/solutions/ocean-sensor-platform/how-it-works | Spotter – How It Works | Static | 1 | Medium | 8 | Yes | Sensor → Model → Forecast explanation
sofarocean.com/solutions/ocean-sensor-platform/use-cases/[slug] | Spotter – Use Cases | Template | 4 | Medium | 8 | Yes | Use case pages for Spotter
sofarocean.com/solutions/ocean-sensor-platform/pricing | Spotter – Pricing | Static | 1 | Low | 6 | Yes | Pricing page
sofarocean.com/solutions/ocean-sensor-platform/sound-library | Spotter – Sound Library | Collection | 1 | Medium | 10 | Yes | Sound library — filterable CMS collection
sofarocean.com/products/spotter/[sensor] | Spotter Sensors | Template | 9 | Medium | 10 | Yes | hydrophone, DO, pressure, current-meter, bristlemouth, etc.
SOLUTIONS — WEATHER & FORECASTING
sofarocean.com/solutions/weather-forecasting | Weather | Static | 1 | High | 16 | Yes | Dashboard overview: real-time forecast samples, screenshots, models
sofarocean.com/solutions/weather-forecasting/accuracy | Weather – Accuracy | Static | 1 | Medium | 8 | Yes | Forecast accuracy & validation: metrics vs. competitors
sofarocean.com/solutions/weather-forecasting/meet-the-scientist | Weather – Scientist | Static | 1 | Low | 6 | Yes | Meet the Scientist editorial page
sofarocean.com/solutions/weather-forecasting/use-cases/[slug] | Weather – Use Cases | Template | 3 | Medium | 8 | Yes | Use case pages for Weather & Forecasting
SOLUTIONS — DEFENCE & GOVERNMENT
sofarocean.com/solutions/defence-government | Defence | Static | 1 | High | 16 | Yes | Mission applications, partnerships & certifications, secure inquiry form
sofarocean.com/solutions/defence-government/mission-applications | Defence – Missions | Static | 1 | Medium | 8 | Yes | Mission applications sub-page
sofarocean.com/solutions/defence-government/partnerships | Defence – Partnerships | Static | 1 | Medium | 6 | Yes | Partnerships & certifications
RESOURCES
sofarocean.com/case-studies | Resources – Case Studies | Collection | 1 | Medium | 8 | Yes | Filterable by persona (Fleet ¦ Research ¦ Defence)
sofarocean.com/case-studies/[slug] | Case Study | Template | 10 | Medium | 8 | Yes | Case study detail template
sofarocean.com/webinars-events | Resources – Events | Collection | 1 | Medium | 8 | Yes | Webinars & events listing
sofarocean.com/updates | Blog / Newsroom | Collection | 1 | Medium | 8 | Yes | Blog listing with filtering
sofarocean.com/posts/[slug] | Blog Post | Template | 200+ | Medium | 10 | Yes | Post template — text, media, author
sofarocean.com/research-papers | Resources – Research | Collection | 1 | Medium | 8 | Yes | Research papers & white papers listing
sofarocean.com/research-papers/[slug] | Research Paper | Template | 15 | Low | 6 | Yes | Research paper / white paper detail page
ABOUT
sofarocean.com/company/about | About | Static | 1 | Medium | 8 | Yes | Team/company overview
sofarocean.com/data-philosophy | About | Static | 1 | Medium | 8 | Yes | Data philosophy editorial page
sofarocean.com/sustainability | About | Static | 1 | Medium | 8 | Yes | Sustainability / impact — environmental and social initiatives
sofarocean.com/company/careers | About | Static | 1 | Medium | 8 | Yes | Job listings — may integrate ATS
sofarocean.com/legal/[page] | Legal | Template | 7 | Low | 4 | Yes | Terms, privacy, compliance pages
SIGNUP / CONVERSION
sofarocean.com/signup/[form] | Signup/Demo | Template | 10+ | Medium | 8 | Yes | Demo forms, partner signups — persona-specific CTAs
|  |  | TOTAL UNIQUE BUILDS |  | #VALUE!
|  |  | Content Migration (200+ posts, research papers, case studies) |  | 80
|  |  | TOTAL PAGE HOURS |  | 410

## Dev Only
PROJECT PLAN
Sprint | Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4 |  | Sprint 5 |  | Sprint 6 |  | Support
Date | 2026-03-03 | 2026-03-10 | 2026-03-17 | 2026-03-24 | 2026-03-31 | 2026-04-07 | 2026-04-14 | 2026-04-21 | 2026-04-28 | 2026-05-05 | 2026-05-12 | 2026-05-19 | 2026-05-26 | 2026-06-02
Project Setup | Project Setup
Development |  | Frontend Dev
Animations |  |  |  | Motion/Interaction
Content Migration |  |  |  |  | Content Migration
SEO | SEO Audit |  |  | SEO Setup |  |  | SEO Setup |  | SEO Setup
QA |  |  |  | QA |  | QA |  | QA |  | QA | QA
Design Consulting | Design Consulting
Enablement | [9 empty] | Enablement
HOURLY BREAKDOWN
Totals
Role |  | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12 | Wk13 | Wk14
Project Manager | 56 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Webflow Developer | 158 | 0 | 8 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 6 | 0 | 0
Motion Developer | 48 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0
Data/Content Team | 40 | 0 | 0 | 0 | 0 | 4 | 8 | 8 | 8 | 4 | 4 | 4 | 0 | 0 | 0
SEO Specialist | 32 | 8 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 4 | 4 | 4 | 4 | 0 | 0
QA Specialist | 24 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 4 | 4 | 0 | 0
Design Consultant | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 374 | 20 | 20 | 20 | 36 | 32 | 40 | 40 | 40 | 36 | 32 | 32 | 18 | 4 | 4
TEAM OVERVIEW |  | Wk4: OVERVIEW TABLE; Wk10: COST BREAKDOWN
Role | Rate | Wk10: Work Stream; Wk13: Total Hours; Wk14: Cost
Project Manager | 195 | Wk4: Start Date; Wk8: 2026-03-03; Wk10: Project Management; Wk13: 56; Wk14: 8400
Webflow Developer | 175 | Wk4: Handoff Date; Wk8: 2026-05-26; Wk10: Webflow Development; Wk13: 158; Wk14: 23700
Motion Developer | 195 | Wk4: Weeks; Wk8: 12; Wk10: Motion/Interaction Dev; Wk13: 48; Wk14: 7200
SEO Specialist | 225 | Wk4: Days; Wk8: 84; Wk10: Content Migration; Wk13: 40; Wk14: 6000
QA Specialist | 140 | Wk4: Blended Rate; Wk8: 184.6089; Wk10: SEO Setup; Wk13: 32; Wk14: 4800
Design Consultant | 195 | Wk4: Standard Rate (MSA); Wk8: 150; Wk10: Quality Assurance; Wk13: 24; Wk14: 3600
Data/Content Team | 140 | Wk4: Hours Total; Wk8: 374; Wk10: Design Consulting; Wk13: 16; Wk14: 2400
[5 empty] | Hours Weekly |  |  |  | 31.1667
[5 empty] | Weekly Run Rate |  |  |  | 4675 |  | Total |  |  | 374 | 56100
[5 empty] | Budget Per Sprint |  |  |  | 9350
[5 empty] | Total |  |  |  | 56100

## Full Service
PROJECT PLAN
Sprint | Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4 |  | Sprint 5 |  | Sprint 6 |  | Sprint 7 |  | Sprint 8 |  | Sprint 9 |  | Support
Date | 2026-03-03 | 2026-03-10 | 2026-03-17 | 2026-03-24 | 2026-03-31 | 2026-04-07 | 2026-04-14 | 2026-04-21 | 2026-04-28 | 2026-05-05 | 2026-05-12 | 2026-05-19 | 2026-05-26 | 2026-06-02 | 2026-06-09 | 2026-06-16 | 2026-06-23 | 2026-06-30 | 2026-07-07 | 2026-07-14
DESIGN PHASE
Discovery & IA | Discovery | Discovery | IA & Sitemap | IA & Sitemap
UX / Wireframes |  |  | Wireframes | Wireframes | Wireframes | Wireframes
UI Design |  |  |  |  | Visual Design | Visual Design | Visual Design | Visual Design
Motion Concepts | [6 empty] | Motion Direction | Motion Direction
Design Review |  |  |  | Review |  | Review |  | Review/Handoff
DEV PHASE
Project Setup | [8 empty] | Project Setup
Development | [9 empty] | Frontend Dev | Frontend Dev | Frontend Dev | Frontend Dev | Frontend Dev | Frontend Dev | Frontend Dev | Frontend Dev
Motion Dev | [11 empty] | Motion/Interaction | Motion/Interaction | Motion/Interaction
Content Migration | [12 empty] | Content Migration | Content Migration | Content Migration | Content Migration
SEO | [8 empty] | SEO Audit |  |  |  | SEO Setup |  | SEO Setup |  | SEO Setup
QA | [11 empty] | QA |  | QA |  | QA | QA | QA
Enablement | [16 empty] | Enablement | Enablement
HOURLY BREAKDOWN
Role | Totals | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12 | Wk13 | Wk14 | Wk15 | Wk16 | Wk17 | Wk18
Project Manager | 72 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
UX Designer | 80 | 8 | 8 | 12 | 12 | 12 | 12 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UI Designer | 76 | 0 | 0 | 4 | 4 | 12 | 12 | 16 | 16 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
Creative Director | 24 | 4 | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0
Webflow Developer | 136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16
Motion Developer | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 0
Data/Content Team | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 8 | 8 | 8 | 8 | 4
SEO Specialist | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 4 | 4
QA Specialist | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 4 | 4 | 4
Total | 520 | 16 | 16 | 20 | 24 | 28 | 32 | 28 | 32 | 12 | 16 | 24 | 40 | 36 | 40 | 40 | 40 | 44 | 32
TEAM OVERVIEW |  |  |  |  | OVERVIEW TABLE | [5 empty] | COST BREAKDOWN
Role | Rate | [9 empty] | Work Stream |  | Total Hours | Cost
Project Manager | 195 |  |  |  | Start Date |  |  |  | 2026-03-03 |  | Project Management |  | 72 | 10800
UX Designer | 175 |  |  |  | Handoff Date |  |  |  | 2026-07-14 |  | UX Design |  | 80 | 12000
UI Designer | 175 |  |  |  | Weeks |  |  |  | 19 |  | UI Design |  | 76 | 11400
Creative Director | 225 |  |  |  | Days |  |  |  | 133 |  | Creative Direction |  | 24 | 3600
Motion Developer | 195 |  |  |  | Blended Rate |  |  |  | 186.1923 |  | Webflow Development |  | 48 | 7200
Webflow Developer | 175 |  |  |  | Standard Rate (MSA) |  |  |  | 150 |  | Motion/Interaction Dev |  | 136 | 20400
SEO Specialist | 225 |  |  |  | Hours Total |  |  |  | 520 |  | Content Migration |  | 24 | 3600
QA Specialist | 140 |  |  |  | Hours Weekly |  |  |  | 27.3684 |  | SEO Setup |  | 20 | 3000
Data/Content Team | 140 |  |  |  | Weekly Run Rate |  |  |  | 5095.7895 |  | Quality Assurance |  | 40 | 6000
[5 empty] | Budget Per Sprint |  |  |  | 10191.5789
[5 empty] | Total |  |  |  | 78000 |  | Total |  | 520 | 78000