## Standard Estimator - SALES
|  |  |  | STEP 1 - is this item in or out of scope: |  | STEP 2 - for yellow cells only: | [9 empty] | STEP 3 - add assumptions here in client-friendly language:
Phase | Service | Area | Deliverable | Is this deliverable in scope? | Type (variable quantity or fixed) |  | Enter quantity here | Fixed quantity | Total quantity scoped | Effort per quantity unit (hours) | Total effort scoped for this deliverable (hours) | Rate ($/hr) | Overhead % | Fully Loaded Cost ($) | Min Sell ($) | Assumptions
FOUNDATIONS | Design | Discovery | Kickoff + stakeholder alignment workshop | NO | FIXED |  | 10 | 1 | 0 | 3 | 0 | 40 | 20% | 0 | 0
FOUNDATIONS | Design | Discovery | Competitive website review (per competitor) | NO | VARIABLE | Number of competitor websites to be audited: | 2 |  | 0 | 0.75 | 0 | 40 | 20% | 0 | 0
FOUNDATIONS | Design | Discovery | Design inspiration / moodboard sprint | NO | FIXED |  |  | 1 | 0 | 2 | 0 | 40 | 20% | 0 | 0
FOUNDATIONS | Design | Branding | Brand audit (current guidelines + assets) | NO | FIXED |  |  | 1 | 0 | 3 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | Branding | Logo refinement (light) | NO | FIXED |  |  | 1 | 0 | 6 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | Branding | Logo redesign (full) | NO | FIXED |  |  | 1 | 0 | 12 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | Branding | Color palette system | NO | FIXED |  |  | 1 | 0 | 2 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | Branding | Typography system | NO | FIXED |  |  | 1 | 0 | 2 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | Branding | Iconography style + starter set (10 icons) | NO | FIXED |  |  | 1 | 0 | 4 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | Branding | Illustration style definition | NO | FIXED |  |  | 1 | 0 | 3 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | Branding | Brand guidelines (lite – 10–15 pages) | NO | FIXED |  |  | 1 | 0 | 8 | 0 | 40 | 20% | 0 | 0
FOUNDATIONS | Design | UX | Information architecture + sitemap | NO | FIXED |  |  | 1 | 0 | 4 | 0 | 40 | 20% | 0 | 0
FOUNDATIONS | Design | UX | Wireframes – homepage | NO | FIXED |  |  | 1 | 0 | 4 | 0 | 40 | 20% | 0 | 0 |  | NO
FOUNDATIONS | Design | UX | Wireframes – template page type (per template) | NO | VARIABLE | Number of templates we are assuming: | 10 |  | 0 | 2.5 | 0 | 40 | 20% | 0 | 0
FOUNDATIONS | Design | UX | Form UX (contact/demo) wireframe | NO | FIXED |  |  | 1 | 0 | 1.5 | 0 | 40 | 20% | 0 | 0
FOUNDATIONS | Design | UX | Pricing UX wireframe | NO | FIXED |  |  | 1 | 0 | 2 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | UI System | Figma project setup + page grid | NO | FIXED |  |  | 1 | 0 | 1 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | UI System | UI kit: typography styles | NO | FIXED |  |  | 1 | 0 | 1.5 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | UI System | UI kit: color tokens + semantic roles | NO | FIXED |  |  | 1 | 0 | 1.5 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | UI System | UI kit: spacing scale + layout primitives | NO | FIXED |  |  | 1 | 0 | 1.5 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | UI System | Component design: buttons (states) | NO | FIXED |  |  | 1 | 0 | 1.5 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | UI System | Component design: forms (inputs, selects, errors) | NO | FIXED |  |  | 1 | 0 | 2 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | UI System | Component design: cards (variants) | NO | FIXED |  |  | 1 | 0 | 2 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | UI System | Component design: accordions + tabs | NO | FIXED |  |  | 1 | 0 | 2 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | UI System | Component design: sliders/carousels | NO | FIXED |  |  | 1 | 0 | 2 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | UI System | Component design: pricing table | NO | FIXED |  |  | 1 | 0 | 2.5 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | UI System | Component design: testimonials | NO | FIXED |  |  | 1 | 0 | 1.5 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | UI System | Component design: CTAs (banner, inline, sticky) | NO | FIXED |  |  | 1 | 0 | 1.5 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | UI System | Component design: navigation (desktop) | NO | FIXED |  |  | 1 | 0 | 2 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | UI System | Component design: navigation (mobile) | NO | FIXED |  |  | 1 | 0 | 2 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | UI System | Component design: footer system | NO | FIXED |  |  | 1 | 0 | 2 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | Page UI | Homepage UI design | NO | FIXED |  |  | 1 | 0 | 10 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | Page UI | Pillar / solution page UI design | NO | FIXED |  |  | 1 | 0 | 6 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | Page UI | Use case page UI design | NO | FIXED |  |  | 1 | 0 | 5 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | Page UI | Industry page UI design | NO | FIXED |  |  | 1 | 0 | 5 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | Page UI | Product overview page UI design | NO | FIXED |  |  | 1 | 0 | 6 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | Page UI | Product detail page UI design | NO | FIXED |  |  | 1 | 0 | 6 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | Page UI | Integrations listing page UI design | NO | FIXED |  |  | 1 | 0 | 5 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | Page UI | Integration detail page UI design | NO | FIXED |  |  | 1 | 0 | 5 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | Page UI | Resource hub UI design | NO | FIXED |  |  | 1 | 0 | 6 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | Page UI | Blog listing UI design | NO | FIXED |  |  | 1 | 0 | 4 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | Page UI | Blog article template UI design | NO | FIXED |  |  | 1 | 0 | 4 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | Page UI | Case study template UI design | NO | FIXED |  |  | 1 | 0 | 4 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | Page UI | Case study page UI design (example) | NO | FIXED |  |  | 1 | 0 | 3 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | Page UI | About page UI design | NO | FIXED |  |  | 1 | 0 | 4 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | Page UI | Contact/Demo page UI design | NO | FIXED |  |  | 1 | 0 | 4 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | Page UI | Pricing page UI design | NO | FIXED |  |  | 1 | 0 | 6 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | Page UI | Security/Compliance page UI design | NO | FIXED |  |  | 1 | 0 | 5 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | Page UI | Careers listing UI design | NO | FIXED |  |  | 1 | 0 | 4 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | Page UI | Job detail page UI design | NO | FIXED |  |  | 1 | 0 | 3 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | Page UI | Legal template UI design | NO | FIXED |  |  | 1 | 0 | 2 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | Page UI | 404 page UI design | NO | FIXED |  |  | 1 | 0 | 1.5 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | Graphics | Hero illustration / composite (per page) | NO | VARIABLE | Number of pages needing hero illustration / composite: |  |  | 0 | 3 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | Graphics | Product UI mockup (per screenshot) | NO | VARIABLE | Number of product UI mock up screenshots needed: |  |  | 0 | 0.75 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | Graphics | Feature diagram (per diagram) | NO | VARIABLE | Number of feature diagrams: |  |  | 0 | 1.5 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | Graphics | Background pattern / texture | NO | FIXED |  |  | 1 | 0 | 1 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | Graphics | Image editing + compositing (per image) | NO | VARIABLE | Number of images assumed for edit/compositing: |  |  | 0 | 0.5 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | Graphics | Infographic for webpage | NO | FIXED |  |  | 1 | 0 | 4 | 0 | 40 | 20% | 0 | 0
DELIVERY | Design | Handoff | Design-dev handoff walkthrough | NO | FIXED |  |  | 1 | 0 | 2 | 0 | 40 | 20% | 0 | 0
DESIGN | Design | Handoff | Design QA round (per page) | NO | VARIABLE | Number of pages needing design QA: |  |  | 0 | 0.75 | 0 | 40 | 20% | 0 | 0
FOUNDATIONS | Dev | Foundation | Webflow project setup + environments | NO | FIXED |  |  | 1 | 0 | 2 | 0 | 40 | 20% | 0 | 0
FOUNDATIONS | Dev | Foundation | Domain + DNS coordination (staging) | NO | FIXED |  |  | 1 | 0 | 1 | 0 | 40 | 20% | 0 | 0
FOUNDATIONS | Dev | Foundation | Global style guide build (classes, variables) | NO | FIXED |  |  | 1 | 0 | 8 | 0 | 40 | 20% | 0 | 0
FOUNDATIONS | Dev | Foundation | Component naming + structure conventions | NO | FIXED |  |  | 1 | 0 | 2 | 0 | 40 | 20% | 0 | 0
FOUNDATIONS | Dev | Foundation | Accessibility baseline (focus states, semantics) | NO | FIXED |  |  | 1 | 0 | 3 | 0 | 40 | 20% | 0 | 0
FOUNDATIONS | Dev | Foundation | Analytics baseline (GTM container embed) | NO | FIXED |  |  | 1 | 0 | 1 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Components | Header – simple nav | NO | FIXED |  |  | 1 | 0 | 4 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Components | Header – mega menu | NO | FIXED |  |  | 1 | 0 | 8 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Components | Mobile nav overlay | NO | FIXED |  |  | 1 | 0 | 4 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Components | Footer – basic | NO | FIXED |  |  | 1 | 0 | 2 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Components | Footer – complex (multi-column + CTAs) | NO | FIXED |  |  | 1 | 0 | 6 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Components | Announcement bar | NO | FIXED |  |  | 1 | 0 | 2 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Components | Hero – standard | NO | FIXED |  |  | 1 | 0 | 2.5 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Components | Hero – with tabs/slider | NO | FIXED |  |  | 1 | 0 | 4 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Components | Logos strip | NO | FIXED |  |  | 1 | 0 | 1 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Components | Feature grid (2–4 columns) | NO | FIXED |  |  | 1 | 0 | 2 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Components | Feature list (icon + text) | NO | FIXED |  |  | 1 | 0 | 2 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Components | Stats counters | NO | FIXED |  |  | 1 | 0 | 2 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Components | Testimonial slider | NO | FIXED |  |  | 1 | 0 | 2.5 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Components | Case study teaser card | NO | FIXED |  |  | 1 | 0 | 2 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Components | Pricing table (responsive) | NO | FIXED |  |  | 1 | 0 | 6 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Components | FAQ accordion | NO | FIXED |  |  | 1 | 0 | 2 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Components | CTA banner | NO | FIXED |  |  | 1 | 0 | 1.5 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Components | Modal component | NO | FIXED |  |  | 1 | 0 | 4 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Components | Form component – contact/demo | NO | FIXED |  |  | 1 | 0 | 3 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Components | Tabs component | NO | FIXED |  |  | 1 | 0 | 3 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Components | Table component – responsive | NO | FIXED |  |  | 1 | 0 | 4 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Components | Video embed component | NO | FIXED |  |  | 1 | 0 | 1 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Components | Timeline component | NO | FIXED |  |  | 1 | 0 | 4 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Components | Comparison component | NO | FIXED |  |  | 1 | 0 | 4 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Components | Breadcrumbs | NO | FIXED |  |  | 1 | 0 | 1 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Pages | Homepage build | NO | FIXED |  |  | 1 | 0 | 16 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Pages | Pillar / solution page build | NO | FIXED |  |  | 1 | 0 | 8 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Pages | Use case page build | NO | FIXED |  |  | 1 | 0 | 5 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Pages | Industry page build | NO | FIXED |  |  | 1 | 0 | 5 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Pages | Product overview page build | NO | FIXED |  |  | 1 | 0 | 6 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Pages | Product detail page build | NO | FIXED |  |  | 1 | 0 | 6 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Pages | Integrations listing page build | NO | FIXED |  |  | 1 | 0 | 5 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Pages | Integration detail template build | NO | FIXED |  |  | 1 | 0 | 5 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Pages | Resource hub build | NO | FIXED |  |  | 1 | 0 | 8 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Pages | Blog listing template build | NO | FIXED |  |  | 1 | 0 | 4 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Pages | Blog article template build | NO | FIXED |  |  | 1 | 0 | 6 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Pages | Case study CMS template build | NO | FIXED |  |  | 1 | 0 | 5 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Pages | About page build | NO | FIXED |  |  | 1 | 0 | 5 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Pages | Contact/Demo page build | NO | FIXED |  |  | 1 | 0 | 4 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Pages | Pricing page build | NO | FIXED |  |  | 1 | 0 | 6 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Pages | Security/Compliance page build | NO | FIXED |  |  | 1 | 0 | 4 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Pages | Careers listing build | NO | FIXED |  |  | 1 | 0 | 4 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Pages | Job detail template build | NO | FIXED |  |  | 1 | 0 | 3.5 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Pages | Legal template build | NO | FIXED |  |  | 1 | 0 | 2 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Pages | 404 page build | NO | FIXED |  |  | 1 | 0 | 1.5 | 0 | 40 | 20% | 0 | 0
FOUNDATIONS | Dev | CMS | CMS architecture planning + mapping | NO | FIXED |  |  | 1 | 0 | 4 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | CMS | Create CMS collection (per collection) | NO | VARIABLE | Number of CMS collections: |  |  | 0 | 1.5 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | CMS | CMS field mapping (per collection) | NO | VARIABLE | Number of CMS collections: |  |  | 0 | 1.5 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | CMS | Build CMS template (per template) | NO | VARIABLE | Number of CMS templates: |  |  | 0 | 6 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | CMS | CMS filters/search (basic) | NO | FIXED |  |  | 1 | 0 | 3 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | CMS | CMS pagination (native) | NO | FIXED |  |  | 1 | 0 | 1.5 | 0 | 40 | 20% | 0 | 0
FOUNDATIONS | Dev | Migration | Content migration planning + export | NO | FIXED |  |  | 1 | 0 | 4 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Migration | Content migration (per 10 pages) | NO | VARIABLE | Batches of 10 pages: |  |  | 0 | 6 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Migration | Content migration QA (per 10 pages) | NO | VARIABLE | Batches of 10 pages: |  |  | 0 | 2 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Migration | 301 redirect mapping (per 50 URLs) | NO | VARIABLE | Batches of 50 URLs: |  |  | 0 | 2 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Migration | Redirect implementation + validation | NO | FIXED |  |  | 1 | 0 | 2 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Animations | Webflow interactions (simple per page) | NO | VARIABLE | Number of webflow interactions per page (simple): |  |  | 0 | 1 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Animations | Webflow interactions (complex per page) | NO | VARIABLE | Number of webflow interactions per page (complex): |  |  | 0 | 3 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Animations | Custom JS interaction (per feature) | NO | VARIABLE | Number of custom JS interaction features: |  |  | 0 | 4 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Animations | Lottie integration (per animation) | NO | VARIABLE | Number of Lottie integations per animation: |  |  | 0 | 0.75 | 0 | 40 | 20% | 0 | 0
FOUNDATIONS | Dev | Integrations | GA4 + GTM setup + verification | NO | FIXED |  |  | 1 | 0 | 2 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Integrations | Conversion events setup (per event) | NO | VARIABLE | Number of conversion events: |  |  | 0 | 0.5 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Integrations | HubSpot forms embed (per form) | NO | VARIABLE | Number of Hubspot form embeds: |  |  | 0 | 0.5 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Integrations | Marketo form embed (per form) | NO | VARIABLE | Number of Marketo form embeds: |  |  | 0 | 0.75 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Integrations | Calendly / scheduling embed | NO | FIXED |  |  | 1 | 0 | 0.5 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Integrations | Cookie consent banner + tagging rules | NO | FIXED |  |  | 1 | 0 | 2 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Integrations | Search Console verification + sitemap submit | NO | FIXED |  |  | 1 | 0 | 1 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Integrations | Bing Webmaster Tools setup | NO | FIXED |  |  | 1 | 0 | 0.5 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Integrations | Hotjar / MS Clarity install | NO | FIXED |  |  | 1 | 0 | 0.5 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | QA | Responsive QA (mobile/tablet) | NO | FIXED |  |  | 1 | 0 | 3 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | QA | Accessibility QA pass (WCAG basics) | NO | FIXED |  |  | 1 | 0 | 3 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | QA | Content QA + link check | NO | FIXED |  |  | 1 | 0 | 2.5 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | QA | Pre-launch checklist + stakeholder signoff | NO | FIXED |  |  | 1 | 0 | 2 | 0 | 40 | 20% | 0 | 0
LAUNCH | Dev | Launch | Launch support window | NO | FIXED |  |  | 1 | 0 | 3 | 0 | 40 | 20% | 0 | 0
LAUNCH | Dev | Launch | Post-launch monitoring (24–48h) | NO | FIXED |  |  | 1 | 0 | 2 | 0 | 40 | 20% | 0 | 0
DELIVERY | Dev | Backend | CRM sync (HubSpot/Salesforce) – custom | NO | FIXED |  |  | 1 | 0 | 8 | 0 | 80 | 20% | 0 | 0
FOUNDATIONS | Growth | WAIO | WAIO framework workshop + requirements | NO | FIXED |  |  | 1 | 0 | 4 | 0 | 40 | 20% | 0 | 0
FOUNDATIONS | Growth | WAIO | WAIO implementation plan + backlog | NO | FIXED |  |  | 1 | 0 | 3 | 0 | 40 | 20% | 0 | 0
DELIVERY | Growth | WAIO | WAIO template recommendations (per template) | NO | FIXED |  |  | 1 | 0 | 2 | 0 | 40 | 20% | 0 | 0
[11 empty] | 0 |  |  |  | 0

## Output to go into proposal appe
PROPOSAL APPENDIX: Agreed project scope | [5 empty] | Use this column to filter for YES once scope is agreed, then copy and paste columns A to F to proposal appendix
Service | Area | Deliverable |  |  | Assumptions | Is this deliverable in scope?
Design | Discovery | Kickoff + stakeholder alignment workshop |  |  |  | NO
Design | Discovery | Competitive website review (per competitor) | Number of competitor websites to be audited: | 2 |  | NO
Design | Discovery | Design inspiration / moodboard sprint |  |  |  | NO
Design | Branding | Brand audit (current guidelines + assets) |  |  |  | NO
Design | Branding | Logo refinement (light) |  |  |  | NO
Design | Branding | Logo redesign (full) |  |  |  | NO
Design | Branding | Color palette system |  |  |  | NO
Design | Branding | Typography system |  |  |  | NO
Design | Branding | Iconography style + starter set (10 icons) |  |  |  | NO
Design | Branding | Illustration style definition |  |  |  | NO
Design | Branding | Brand guidelines (lite – 10–15 pages) |  |  |  | NO
Design | UX | Information architecture + sitemap |  |  |  | NO
Design | UX | Wireframes – homepage |  |  |  | NO
Design | UX | Wireframes – template page type (per template) | Number of templates we are assuming: | 10 |  | NO
Design | UX | Form UX (contact/demo) wireframe |  |  |  | NO
Design | UX | Pricing UX wireframe |  |  |  | NO
Design | UI System | Figma project setup + page grid |  |  |  | NO
Design | UI System | UI kit: typography styles |  |  |  | NO
Design | UI System | UI kit: color tokens + semantic roles |  |  |  | NO
Design | UI System | UI kit: spacing scale + layout primitives |  |  |  | NO
Design | UI System | Component design: buttons (states) |  |  |  | NO
Design | UI System | Component design: forms (inputs, selects, errors) |  |  |  | NO
Design | UI System | Component design: cards (variants) |  |  |  | NO
Design | UI System | Component design: accordions + tabs |  |  |  | NO
Design | UI System | Component design: sliders/carousels |  |  |  | NO
Design | UI System | Component design: pricing table |  |  |  | NO
Design | UI System | Component design: testimonials |  |  |  | NO
Design | UI System | Component design: CTAs (banner, inline, sticky) |  |  |  | NO
Design | UI System | Component design: navigation (desktop) |  |  |  | NO
Design | UI System | Component design: navigation (mobile) |  |  |  | NO
Design | UI System | Component design: footer system |  |  |  | NO
Design | Page UI | Homepage UI design |  |  |  | NO
Design | Page UI | Pillar / solution page UI design |  |  |  | NO
Design | Page UI | Use case page UI design |  |  |  | NO
Design | Page UI | Industry page UI design |  |  |  | NO
Design | Page UI | Product overview page UI design |  |  |  | NO
Design | Page UI | Product detail page UI design |  |  |  | NO
Design | Page UI | Integrations listing page UI design |  |  |  | NO
Design | Page UI | Integration detail page UI design |  |  |  | NO
Design | Page UI | Resource hub UI design |  |  |  | NO
Design | Page UI | Blog listing UI design |  |  |  | NO
Design | Page UI | Blog article template UI design |  |  |  | NO
Design | Page UI | Case study template UI design |  |  |  | NO
Design | Page UI | Case study page UI design (example) |  |  |  | NO
Design | Page UI | About page UI design |  |  |  | NO
Design | Page UI | Contact/Demo page UI design |  |  |  | NO
Design | Page UI | Pricing page UI design |  |  |  | NO
Design | Page UI | Security/Compliance page UI design |  |  |  | NO
Design | Page UI | Careers listing UI design |  |  |  | NO
Design | Page UI | Job detail page UI design |  |  |  | NO
Design | Page UI | Legal template UI design |  |  |  | NO
Design | Page UI | 404 page UI design |  |  |  | NO
Design | Graphics | Hero illustration / composite (per page) | Number of pages needing hero illustration / composite: |  |  | NO
Design | Graphics | Product UI mockup (per screenshot) | Number of product UI mock up screenshots needed: |  |  | NO
Design | Graphics | Feature diagram (per diagram) | Number of feature diagrams: |  |  | NO
Design | Graphics | Background pattern / texture |  |  |  | NO
Design | Graphics | Image editing + compositing (per image) | Number of images assumed for edit/compositing: |  |  | NO
Design | Graphics | Infographic for webpage |  |  |  | NO
Design | Handoff | Design-dev handoff walkthrough |  |  |  | NO
Design | Handoff | Design QA round (per page) | Number of pages needing design QA: |  |  | NO
Dev | Foundation | Webflow project setup + environments |  |  |  | NO
Dev | Foundation | Domain + DNS coordination (staging) |  |  |  | NO
Dev | Foundation | Global style guide build (classes, variables) |  |  |  | NO
Dev | Foundation | Component naming + structure conventions |  |  |  | NO
Dev | Foundation | Accessibility baseline (focus states, semantics) |  |  |  | NO
Dev | Foundation | Analytics baseline (GTM container embed) |  |  |  | NO
Dev | Components | Header – simple nav |  |  |  | NO
Dev | Components | Header – mega menu |  |  |  | NO
Dev | Components | Mobile nav overlay |  |  |  | NO
Dev | Components | Footer – basic |  |  |  | NO
Dev | Components | Footer – complex (multi-column + CTAs) |  |  |  | NO
Dev | Components | Announcement bar |  |  |  | NO
Dev | Components | Hero – standard |  |  |  | NO
Dev | Components | Hero – with tabs/slider |  |  |  | NO
Dev | Components | Logos strip |  |  |  | NO
Dev | Components | Feature grid (2–4 columns) |  |  |  | NO
Dev | Components | Feature list (icon + text) |  |  |  | NO
Dev | Components | Stats counters |  |  |  | NO
Dev | Components | Testimonial slider |  |  |  | NO
Dev | Components | Case study teaser card |  |  |  | NO
Dev | Components | Pricing table (responsive) |  |  |  | NO
Dev | Components | FAQ accordion |  |  |  | NO
Dev | Components | CTA banner |  |  |  | NO
Dev | Components | Modal component |  |  |  | NO
Dev | Components | Form component – contact/demo |  |  |  | NO
Dev | Components | Tabs component |  |  |  | NO
Dev | Components | Table component – responsive |  |  |  | NO
Dev | Components | Video embed component |  |  |  | NO
Dev | Components | Timeline component |  |  |  | NO
Dev | Components | Comparison component |  |  |  | NO
Dev | Components | Breadcrumbs |  |  |  | NO
Dev | Pages | Homepage build |  |  |  | NO
Dev | Pages | Pillar / solution page build |  |  |  | NO
Dev | Pages | Use case page build |  |  |  | NO
Dev | Pages | Industry page build |  |  |  | NO
Dev | Pages | Product overview page build |  |  |  | NO
Dev | Pages | Product detail page build |  |  |  | NO
Dev | Pages | Integrations listing page build |  |  |  | NO
Dev | Pages | Integration detail template build |  |  |  | NO
Dev | Pages | Resource hub build |  |  |  | NO
Dev | Pages | Blog listing template build |  |  |  | NO
Dev | Pages | Blog article template build |  |  |  | NO
Dev | Pages | Case study CMS template build |  |  |  | NO
Dev | Pages | About page build |  |  |  | NO
Dev | Pages | Contact/Demo page build |  |  |  | NO
Dev | Pages | Pricing page build |  |  |  | NO
Dev | Pages | Security/Compliance page build |  |  |  | NO
Dev | Pages | Careers listing build |  |  |  | NO
Dev | Pages | Job detail template build |  |  |  | NO
Dev | Pages | Legal template build |  |  |  | NO
Dev | Pages | 404 page build |  |  |  | NO
Dev | CMS | CMS architecture planning + mapping |  |  |  | NO
Dev | CMS | Create CMS collection (per collection) | Number of CMS collections: |  |  | NO
Dev | CMS | CMS field mapping (per collection) | Number of CMS collections: |  |  | NO
Dev | CMS | Build CMS template (per template) | Number of CMS templates: |  |  | NO
Dev | CMS | CMS filters/search (basic) |  |  |  | NO
Dev | CMS | CMS pagination (native) |  |  |  | NO
Dev | Migration | Content migration planning + export |  |  |  | NO
Dev | Migration | Content migration (per 10 pages) | Batches of 10 pages: |  |  | NO
Dev | Migration | Content migration QA (per 10 pages) | Batches of 10 pages: |  |  | NO
Dev | Migration | 301 redirect mapping (per 50 URLs) | Batches of 50 URLs: |  |  | NO
Dev | Migration | Redirect implementation + validation |  |  |  | NO
Dev | Animations | Webflow interactions (simple per page) | Number of webflow interactions per page (simple): |  |  | NO
Dev | Animations | Webflow interactions (complex per page) | Number of webflow interactions per page (complex): |  |  | NO
Dev | Animations | Custom JS interaction (per feature) | Number of custom JS interaction features: |  |  | NO
Dev | Animations | Lottie integration (per animation) | Number of Lottie integations per animation: |  |  | NO
Dev | Integrations | GA4 + GTM setup + verification |  |  |  | NO
Dev | Integrations | Conversion events setup (per event) | Number of conversion events: |  |  | NO
Dev | Integrations | HubSpot forms embed (per form) | Number of Hubspot form embeds: |  |  | NO
Dev | Integrations | Marketo form embed (per form) | Number of Marketo form embeds: |  |  | NO
Dev | Integrations | Calendly / scheduling embed |  |  |  | NO
Dev | Integrations | Cookie consent banner + tagging rules |  |  |  | NO
Dev | Integrations | Search Console verification + sitemap submit |  |  |  | NO
Dev | Integrations | Bing Webmaster Tools setup |  |  |  | NO
Dev | Integrations | Hotjar / MS Clarity install |  |  |  | NO
Dev | QA | Responsive QA (mobile/tablet) |  |  |  | NO
Dev | QA | Accessibility QA pass (WCAG basics) |  |  |  | NO
Dev | QA | Content QA + link check |  |  |  | NO
Dev | QA | Pre-launch checklist + stakeholder signoff |  |  |  | NO
Dev | Launch | Launch support window |  |  |  | NO
Dev | Launch | Post-launch monitoring (24–48h) |  |  |  | NO
Dev | Backend | CRM sync (HubSpot/Salesforce) – custom |  |  |  | NO
Growth | WAIO | WAIO framework workshop + requirements |  |  |  | NO
Growth | WAIO | WAIO implementation plan + backlog |  |  |  | NO
Growth | WAIO | WAIO template recommendations (per template) |  |  |  | NO

## Project Scope and Pricing Table
| EFFORT (hours) |  |  | COMMERCIALS ($)
| Total effort scoped for deliverables per phase (hours) | 20% allowance for PM/AM (hours) | Total effort (hours) | Minimum charge rate ($) | Minimum cost per phase ($) | Growth lead commercial adjustment ($) | Cost to quote to client ($)
FOUNDATIONS | 0 | 0 | 0 | 40 | 0 | 0 | 0
DESIGN | 0 | 0 | 0 | 40 | 0 | 0 | 0
DELIVERY | 0 | 0 | 0 | 40 | 0 | 0 | 0
LAUNCH | 0 | 0 | 0 | 40 | 0 | 0 | 0
PROJECT TOTAL | 0 | 0 | 0 | 40 | 0 | 0 | 0
Growth lead can apply discount or increase in the yellow cells to achieve target cost to quote to client.
TO DO: Build out GM% calcs here to get better insight into target/guardrail profitability per project
TO DO: Think about how localisation needs incorporating into Standard Estimator - SALES. Lendo project learning.