## SOW Scope Template
Include? | Service | Workstream | SOW Label | Deliverable Summary | Quantity | Notes
| Design | Brand Foundation | Brand Foundation | Brand direction & moodboarding | 1
| Design | UX Strategy | UX Strategy | User journey mapping | 1
| Design | UX Strategy | UX Strategy | Information architecture & sitemap | 1
| Design | UI Design | Core Page Design | Homepage design | 1
| Design | UI Design | Core Page Design | Pillar / core page design | 5
| Design | UI Design | Supporting Page Design | Supporting page design | 4
| Design | Templates | Template Design | Blog/resource template design | 1
| Design | Graphics | Graphic Design | Custom graphics / diagrams | 12
| Design | Motion | Motion Design | Motion direction & micro-interactions | 1
| Dev | Webflow Foundation | Webflow Foundation | Webflow project setup | 1
| Dev | Components | Component Library | Component library build | 12
| Dev | Pages | Core Page Development | Homepage development | 1
| Dev | Pages | Core Page Development | Core page development | 5
| Dev | Pages | Supporting Page Development | Supporting page development | 4
| Dev | CMS | CMS Setup | CMS collection setup | 2
| Dev | CMS | CMS Setup | CMS template development | 2
| Dev | Migration | Content Migration | Content migration | 25
| Dev | Integrations | Integrations | HubSpot form integration | 3
| Dev | Animations | Animation Implementation | Webflow native animations | 6
| Dev | QA & Launch | QA & Launch | QA and launch | 1
| Dev | Backend | Custom Integrations | API integration (non-standard) | 1
| Enablement | Training | Enablement & Training | Webflow CMS training session | 1 session (60–90 mins)
| Enablement | Training | Enablement & Training | Website editing training | 1 session (60 mins)
| Enablement | Enablement | Enablement & Training | Marketing team enablement session | 1 workshop (optional)
| Enablement | Support | Enablement & Training | Post-launch enablement support window | 2 weeks (optional)
| Growth | SEO Foundation | SEO Foundation | Technical SEO foundation | 1
| Growth | SEO Foundation | On-page SEO | On-page SEO optimization | 10
| Growth | Content | Content Strategy | Content outline creation | 10
| Growth | AEO/WAIO | AEO / WAIO | AEO / WAIO baseline | 1
| Growth | CRO Foundation | CRO Foundation | CRO baseline recommendations | 1

## Definition Matrix
Service | Workstream | Deliverable | Definition (What it is) | Included (In Scope) | Not Included (Out of Scope) | Unit Definition | Qty | SOW Label (Client-facing) | Internal Notes
Design | Brand Foundation | Brand direction & moodboarding | Establishes visual direction for the website before UI execution. | Moodboards; visual direction; color/typography alignment; style references | Full rebrand; logo redesign; brand strategy workshops | One phase per project | 1 | Brand Foundation
Design | UX Strategy | User journey mapping | Maps primary user flows to support navigation and conversion. | Primary journeys; conversion paths; high-level UX logic | Full UX research; persona research; usability testing | One mapping phase per project | 1 | UX Strategy
Design | UX Strategy | Information architecture & sitemap | Defines page hierarchy and navigation structure. | Sitemap; nav structure; page grouping | Major IA changes after approval | One sitemap per project | 1 | UX Strategy
Design | UI Design | Homepage design | Design of the primary homepage layout. | Desktop + mobile design; standard states; revisions in scope | Net-new layout concepts beyond approved direction | One unique layout | 1 | Core Page Design
Design | UI Design | Pillar / core page design | Design of primary conversion or solution pages. | Desktop + mobile layout; componentized design | Additional unique layouts beyond quantity | One unique layout | 5 | Core Page Design
Design | UI Design | Supporting page design | Design of secondary pages like pricing, about, contact. | Layout design and responsive states | Complex custom interactions not approved | One unique layout | 4 | Supporting Page Design
Design | Templates | Blog/resource template design | Reusable template for CMS-driven content. | Template layout for blog/resource items | Unique designs per CMS item | One template | 1 | Template Design
Design | Graphics | Custom graphics / diagrams | Custom visual assets for pages. | Diagrams; product visuals; icon compositions | 3D renders; video production | Per asset | 12 | Graphic Design
Design | Motion | Motion direction & micro-interactions | Defines motion style and interaction intent. | Simple motion direction; interaction notes | Complex animation production | One phase | 1 | Motion Design
Dev | Webflow Foundation | Webflow project setup | Initial project setup and baseline configuration in Webflow. | Project setup; global styles; breakpoints; basic accessibility | Hosting setup outside Webflow; backend infra | One setup per project | 1 | Webflow Foundation
Dev | Components | Component library build | Reusable components based on approved designs. | Cards; sections; CTAs; forms; nav blocks | Net-new components after approval | Per component | 12 | Component Library
Dev | Pages | Homepage development | Build of homepage in Webflow from approved design. | Responsive build; standard interactions | Redesign during development | One unique layout | 1 | Core Page Development
Dev | Pages | Core page development | Build of pillar/solution pages. | Responsive build; componentized sections | Additional unique layouts beyond quantity | One unique layout | 5 | Core Page Development
Dev | Pages | Supporting page development | Build of supporting pages (about/contact/pricing/etc.). | Responsive build and QA | Custom app-like functionality | One unique layout | 4 | Supporting Page Development
Dev | CMS | CMS collection setup | Configuration of CMS collections and fields. | Collection creation; fields; basic relations | Complex relational databases | Per collection | 2 | CMS Setup
Dev | CMS | CMS template development | Development of CMS templates. | Template build for CMS items | Unique design per item | Per template | 2 | CMS Setup
Dev | Migration | Content migration | Migration of existing content into Webflow templates. | Copy/paste migration; formatting cleanup | Copywriting; SEO rewriting | Per page migrated | 25 | Content Migration
Dev | Integrations | HubSpot form integration | Embedding and styling HubSpot forms. | Embed; styling; mapping basic fields | Custom backend logic | Per form | 3 | Integrations
Dev | Animations | Webflow native animations | Implementation of approved native animations. | Scroll interactions; hover; load animations | Custom JS animation frameworks | Per animation group | 6 | Animation Implementation
Dev | QA & Launch | QA and launch | Final QA, testing and launch support. | Cross-device QA; fixes; launch checklist | Post-launch redesigns | One phase | 1 | QA & Launch
Dev | Backend | API integration (non-standard) | Custom API or backend integration work. | Endpoint integration; mapping; testing | Complex backend system architecture | Per integration | 1 | Custom Integrations
Enablement | Training | Webflow CMS training session | Live training session teaching client team how to manage CMS content in Webflow. | CMS editing walkthrough; adding new items; updating content; publishing workflow; Q&A. | Advanced Webflow development training; custom development; strategy consulting. | One live training session (60–90 minutes). | 1 | Enablement & Training
Enablement | Training | Website editing training | Training focused on day-to-day website updates and content management. | Editing text/images; updating pages; basic SEO fields; publishing best practices. | Design changes; layout modifications; dev-level edits. | One live training session (60 minutes). | 1 | Enablement & Training
Enablement | Enablement | Marketing team enablement session | Strategic enablement session helping internal teams operate the new website effectively. | Best practices; governance guidelines; content publishing workflow; ownership recommendations. | Ongoing consulting or growth strategy execution. | One workshop session (60–90 minutes). | 1 | Enablement & Training
Enablement | Support | Post-launch enablement support window | Short-term support period after launch to help client transition ownership. | Clarifications; minor guidance; small adjustments within training scope. | New features; redesign; development requests. | Per week of enablement support. | 2 | Enablement & Training
Growth | SEO Foundation | Technical SEO foundation | Baseline technical SEO setup for launch. | Metadata framework; indexing; sitemap; basic schema | Ongoing SEO strategy | Site-wide | 1 | SEO Foundation
Growth | SEO Foundation | On-page SEO optimization | Optimization of page structure and metadata. | Titles; metas; heading structure; internal links | Copywriting | Per page | 10 | On-page SEO
Growth | Content | Content outline creation | SEO-driven outline recommendations for pages. | Heading structure; topic guidance; keyword direction | Writing full copy | Per page | 10 | Content Strategy
Growth | AEO/WAIO | AEO / WAIO baseline | AI-search readiness and semantic structure setup. | FAQ schema; entity alignment; semantic structure | Ongoing AI optimization | Site-wide | 1 | AEO / WAIO
Growth | CRO Foundation | CRO baseline recommendations | Initial conversion review and recommendations. | Heuristic review; priority recommendations | Ongoing testing program | One audit | 1 | CRO Foundation